## Tidsregistrering
TIDSREGISTRERING FOR PTE-PROJEKTET (6-3-2017 - 24-3-2017)
Navn: | Morten K. Andersen
Dato: | Rolle: | Aktivitet: | Starttid: | Sluttid: | Samlet tid brugt (timer):
2017-03-06 |  | Rollefordeling | 08.05 | 08.30 | 25 min
2017-03-06 |  | Risikoanalyse | 08.30 | 13.30 | 5 timer
2017-03-06 |  | Møde | 14.00 | 14.30 | 30 min
2017-03-07 |  | Renskrive Use-case diagram | 08.15 | 09.15 | 1 time
2017-03-07 |  | Beskriv UC1 (AD, Mockup, Test) |  |  | ?
2017-03-07 |  | prototype for eksekverbar java |  |  | 15 min
2017-03-07 |  | beskriv UC5 (Dom, UC, Mock-up, test) | 10.30 | 11.30 | 1 time
2017-03-07 |  | Udfør brugertest |  |  | ?
2017-03-07 |  | design GUI fra UC1 og UC2 | 14.30 | 15.30 | 1 time
2017-03-10 |  | integrer GUI og logik | 14.30 | 17.00 | 2 timer 30 min
2017-03-13 |  | SSD for UC4 | 10.45 | 11.10 | 25 min
? |  | Review SSD for UC4 | 12.30 | 12.40 | 10 min
? |  | Test Suite OC1 | 12.40 (fredag) | 09.15 (mandag) | ?
? |  | Design OC1 (SD1, DCD1) | 08.40 | 11.30 | 2 timer 50 min
? |  | Review kode til OC4 | 13.45 | 16.00 | 2 timer 15 min
? |  | implementer OC2 | 12.25 | 14.05 | 1 time 40 min
? |  | Review OC7 | 13.00 | 13.25 | 25 min
? |  | Review testsuite OC7 | 14.20 | 15.15 | 55 min
? |  | Lav OC6 | 12.15 | 12.45 | 30 min
2017-03-14 |  | Brugertest 2 | 08.05 | 11.00 | 2 timer 55 min
2017-03-15 |  | Review testsuite OC5 | 08.40 | 09.15 | 35 min
2017-03-15 |  | Review OC5 | 09.30 | 10.00 | 30 min
2017-03-15 |  | Review SSD for UC8 | 10.10 | 10.20 | 10 min
2017-03-15 |  | Review test suite OC6 | 10.30 | 11.00 | 30 min
2017-03-15 |  | Test til svg-fil og tilføjelse af metode + billede | 12.15 | 13.30 | 1 time 15 min
2017-03-15 |  | Dokumenter arbejde | 13.45 | 14.15 | 30 min
2017-03-15 |  | Lav OC5 (DCD, SD) | 14.20 | 15.20 | 1 time
2017-03-17 |  | Test og implementering af super- og subString | 08.20 | 11.20 | 3 timer
2017-03-17 |  | lav felter gule | 12.00 | 13.15 | 1 time 15 min
2017-03-20 |  | projekt manenger (lav post-it's) | 08.15 | 10.30 | 2 timer 15 min
2017-03-20 |  | Lav UC9 (DCD, SD) | 10.30 | 11.45 | 1 time 15 min
2017-03-20 |  | forsæt på at lave UC9 (DCD, SD) | 12.00 | 13.30 | 1 time 30 min
2017-03-20 |  | Implementer TestSuite OC 10 | 14.00 | 15.20 | 1 time 20 min
2017-03-21 |  | review design OC10 | 08.20 | 09.20 | 1 time
2017-03-21 |  | implementation af OC 9 | 09.30 | 11.00 | 1 time 30 min
2017-03-21 |  | implementation af OC 13 | 12.00 | 13.30 | 1 time 30 min
2017-03-21 |  | implementation af OC 14 | 13.30 | 13.40 | 10 min
2017-03-21 |  | implementation af OC 15 | 13.40 | 17.00 | 3 timer 20 min
2017-03-22 |  | Fixing komma til punktum | 08.20 | 10.20 | 1 time 20 min
2017-03-22 |  | Review kode til OC | 10.25 | 10.35 | 10 min
2017-03-22 |  | Lav testcase til beregnSigmaN | 10.45 | 12.25 | 1 time 40 min
2017-03-22 |  | Review getSigmaB OC16 | 12.25 | 13.05 | 40 min
2017-03-22 |  | Hjælp Dan med bugfixing | 13.10 | 13.30 | 20 min
2017-03-22 |  | Funktionalitet på "slet alt" knap + test (hjælp imellem) | 13.30 | 15.00 | 1 time 30 min
2017-03-22 |  | bugfix + implementation | 15.00 | 16.00 | 30 min
2017-03-23 |  | hjælp med at lave kørselsGuide | 08.15 | 09.00 | 45 min
2017-03-23 |  | test af PteCalcController | 09.10 | 12.30 | 3 timer 20 min
2017-03-23 |  | bugfix pdf | 13.50 | 14.50 | 1 time

## Hjælp til rollevalg
* Hvis du er i tvivl om din rolle, så kig i Appendiks A i "Rational Unified Process" (PDF side: 304 - 310) Bogen side 273 - 280)

## Deltagere
Morten K. Andersen
Steffen S. Andersen
Jeppe Damborg
Henrik S. Jørgensen
Tolga Y. Kücük
Ulla Larsen
Jurijs Mahtodujs
Christoffer A. Mørch
Maibritt R. Nielsen
Simon E.H. Nielsen
Nada H. A. Omer
Laura Poyner
Dennis K. Rasmussen
Dennis S. Rosenkilde
Allan Strange
Dan A. Toft

## Gyldige roller
Any Role
Business Designer
Business-Process Analyst
Capsule Designer
Change Control Manager
Configuration Manager
Course Developer
Database Designer
Deployment Manager
Designer
Graphic Artist
Implementer
Integrator
Management Reviewer
Process Engineer
Project Manager
Requirements Specifier
Review Coordinator
Reviewer
Software Architect
Stakeholder
System Administrator
System Analyst
Technical Writer
Test Analyst
Test Designer
Test Manager
Tester
Tool Specialist
User-Interface Designer